## Sheet1
# | Business Requirement | User Stories | Story Points | Sprint # | Status | Remarks
1 | as received from client | list the user stories corresponding to the BR | Multiple story points for each user story | decide sprint # based on priority | In Progress / Planned / Completed
2 | Apply modern analytics to accurately predict fraudulent applications and customers more likely to default on their loan payments | As a data analyst, I want to generate repots and visualizations to accurately predict loan defaulters beforehand | Reports compares sum of loan defaulters vs: 1. Education level 2. Occuptation 3. Age group | 5 | Completed
3 | Create block diagram | As a data analyst I want to start witht eh high level block diagram | Day 1: High level block diagram creation of overall workflow | 1 | Completed
4 | AWS architecture, cost and starting of EDA process | I want to do the AWS architecture and the assiocated cost estimation today. Then start cleaning the data. | Day 2: AWS architecture & cost estimation with some Cleaning of the raw data - Missing value removal, NAN value replacement, removing outliers | 1 | Completed
5 | Complete cleaning data | I want to finish cleaning the data along with extracting valuable informtation from it | Day 3: Creating Insights, Encoding data non integer/float data to be able to use machien learning models, using various machine learning models. | 1 | Completed
6 | Visualize data on Quicksight | I want to load the cleaned data onto redshift and then visualize it in quicksight | Day 4: Loading cleaned data into Redshift, then visualizaing loaded data by connection redshift to quicksight. | 1 | Completed
7 | Finish documentation | I want to finish the documentation | Day 5: Documentation and presentation creation. | 1 | Completed