## Sheet1
# | User stories | Story points | Testcase | DoD/ Expected Results | Actual Results | Status | Remarks
1 | As a Data analysts, I want to generate a detailed dashboard to easily visualize potential defaulters. I also want to create machien learning models to detect potential defaulters. Accuracy of the models used would also be provided. | The report comprises of a few key factors such as age-group, occupation and education level compared with the defaulters (count of sum and percentage values) | Check for loan approval status depending on occupation, education level and age group | Loan approved or denied conditionally | Inferred from the visualization models | Pass/fail | None
2 | Create block diagram | Day 1: High level block diagram creation of overall workflow | Block diagram | Completed block diagram | Met expected results | Pass | Time provided not enough, had to work overtime.
3 | AWS architecture, cost and starting of EDA process | Day 2: AWS architecture & cost estimation with some Cleaning of the raw data - Missing value removal, NAN value replacement, removing outliers | AWS architecture and cost, Partially cleaned data | Architecture and cost estimation done | Met expected results | Pass | Time provided not enough, had to work overtime.
4 | Complete cleaning data | Day 3: Creating Insights, Encoding data non integer/float data to be able to use machien learning models, usign various machien learning models. | Cleaned and merged final data, complex visualization done in jupyter notebook | fully cleaned and merged data | Met expected results | Pass | Time provided not enough, had to work overtime.
5 | Visualize data on Quicksight | Day 4: Loading cleaned data into Redshift, then visualizaing loaded data by connection redshift to quicksight. | Uploaded data to Redhsift and then chart visualization done on quicksight | loaded data into AWS and then visualized | Met expected results | Pass | Time provided not enough, had to work overtime.
6 | Finish documentation | Day 5: Documentation and presentation creation. | Finalizing presentation and documents. | Finished project | Met expected results | Pass | finished in time